## Sheet1
ID | Task Name | Duration | Start | Finish | Resource Name
1 | New Course Proposals | 16 | 2020-08-21 | 2020-09-12 | Dept. Chairs
2 | Review New Course Proposals | 7 | 2014-09-12 | 2014-09-19 | Principal
3 | Program of Studies Recommendations | 5 | 2014-09-22 | 2014-09-26 | Dept. Chairs
4 | Review New Course Proposals with Central Office | 7 | 2014-09-29 | 2014-10-07 | Principal & Superintendent
5 | Present New Courses to BOE | 1 | 2014-10-07 | 2014-10-07 | Principal
6 | Review Program Studies Changes | 14 | 2014-10-07 | 2014-10-24 | Administrators, Dept. Chairs & HS Guidance
7 | Program Studies Typed | 15 | 2014-10-27 | 2014-11-14 | Principal's secretary
8 | Program Studies Printed & Placed On Line | 16 | 2014-11-14 | 2014-12-05 | Principal's secretary
9 | Course Selection Sheets Developed & Printed | 21 | 2014-11-14 | 2015-01-09 | Assistant Principal & HS Guidance
10 | Team Review of Updated Course Selection Sheets | 6 | 2015-01-09 | 2015-01-16 | Assistant Principal & HS Guidance
11 | 8th Grade Parent Night | 1 | 2015-01-22 | 2015-01-22 | Principal, Assistant Principal & HS Guidance
12 | Program of Studies Copies to Learwood & St. Joe's | 1 | 2015-01-22 | 2015-01-22 | HS Guidance
13 | Learwood Scheduling Info Visit | 1 | 2015-01-22 | 2015-01-22 | Principal, Assistant Principal, Guidance, and Athletic Director
14 | Schedule Info Visit St. Joes | 1 | 2015-01-22 | 2015-01-22 | Principal, Assistant Principal, Guidance, and Athletic Director
15 | Learwood Mock Scheduling Day St. Joe's Mock Scheduling Day | 2 | 2015-02-02 | 2015-02-02 | HS Guidance
16 | Learwood Recommendation Day | 1 | 2015-02-05 | 2015-02-05 | MS Guidance
17 | Learwood Course Selection Sheets Returned to MS | 7 | 2015-02-05 | 2015-02-12 | MS Guidance
18 | 9th Grade Scheduling Meeting 12th Period PAC | 1 | 2015-02-19 | 2015-02-19 | HS Guidance
19 | 10th Grade Scheduling Meeting 11th Period PAC | 1 | 2015-02-19 | 2015-02-19 | HS Guidance
20 | 11th Grade Scheduling Meeting 10th Period PAC | 1 | 2015-02-19 | 2015-02-19 | HS Guidance
21 | HS Course Recommendation Day HR AM & PM | 1 | 2015-02-20 | 2015-02-20 | Assistant Principal & Guidance
22 | HS Guidance Review and Student Enter Course Requests | 7 | 2015-02-21 | 2015-02-27 | HS Guidance
23 | HS Course Selection Sheets Returned with Parent Sig. | 1 | 2015-02-27 | 2015-02-27 | HS Guidance
24 | Learwood Course Selection Sheets Student Entered | 16 | 2015-02-23 | 2015-03-10 | HS Guidance
25 | Develop Course Needs From Student Request Data | 6 | 2015-03-11 | 2015-03-16 | Principal and Assitant Principals
26 | Final Day for 10/11/12 Grades to appeal class recommendations | 1 | 2015-03-20 | 2015-03-20 | Administrators & HS Guidance
27 | Finalize HS Teaching Staff Needs Based On Data | 5 | 2015-03-11 | 2015-03-16 | Principal and Assitant Principals
28 | Final Approval Teacher Needs By Central Office | 12 | 2015-03-16 | 2015-03-27 | Principal & Superintendent
29 | Department Input on Teaching Assignments | 3 | 2015-03-17 | 2015-03-20 | Dept. Chairs
30 | Master Schedule Creation (2 Days) | 2 | 2015-03-27 | 2015-03-28 | Principal, Assistant Principals, and HS Guidance
31 | Build Master Schedule Input Master Schedule Run Simulations | 28 | 2015-03-28 | 2015-04-24 | Principal, Assistant Principals, and HS Guidance
32 | Final Day for 9th Graders to appeal class recommendations | 1 | 2015-05-01 | 2015-05-01 | Administrators & HS Guidance
33 | Draft Master Schedule to Dept. Chairs for Input | 4 | 2015-05-04 | 2014-05-08 | Staff by department
34 | Give Staff Tentative Teaching Assignments | 1 | 2015-05-28 | 2015-05-28 | Principal and Assistant Princiipals
35 | Work On Remaining Scheduling Problems | 33 | 2015-05-29 | 2015-06-30 | Principal
36 | Create & Mass Add Study Hall, Lab Study Halls | 33 | 2015-05-29 | 2015-06-30 | Assitant Principal
37 | Type Final Draft Master Schedule & Distribute | 5 | 2015-08-10 | 2015-08-15 | Assistant Principal
38 | Print Student Schedules | 1 | 2015-08-17 | 2015-08-17 | Office Staff